## general_report
Issue Type | Key | Summary | Assignee | Test result | Solution
Bug | CATS-1294 | Date picker not visible for date field | robel alazar | passed
Bug | CATS-1293 | Plan list is empty on EW->Historical needs assessment requests. | robel alazar | displays if the plan has HRD created , check when empty
Bug | CATS-1292 | On EW report -> received Food Aid report, submitting blank value causes the application to break. | nigus | error still exist: duplicated date parameter
Bug | CATS-1291 | The year 2016 is not visible in the drop down box selection. | roble alazar | error page
Bug | CATS-1285 | Saving a blank form causes the application to crash. | nigus | error page
Bug | CATS-1290 | Link broken on EW report. | nigus | passed
Bug | CATS-1284 | Page layout is off | robel alazar | error page
Bug | CATS-1279 | Date filed without date picker | Nathnael Ethan | couldn’t find the report
Bug | CATS-1277 | Reports are not filtered by region. All regions are able to view reports for another region. | Nathnael Ethan | error on the reports : check all regional reports ,missing reports
Bug | CATS-1272 | Regional Request view does' load | robel alazar | comment should be added
Bug | CATS-1274 | could not allocate with the availability of enough stock. | robel alazar | unresolved
Improvement | CATS-1299 | Update Hub UI to be consistent : Hub Events menu | Andinet Asaminew
Improvement | CATS-1298 | Update Hub UI: Starting Balance page to be consistent with other modules | Andinet Asaminew
Improvement | CATS-1297 | Update Hub UI: Incoming Transport Orders page to be consistent with other modules | Andinet Asaminew
Improvement | CATS-1296 | Update Hub UI to be consistent :Dispatch | Andinet Asaminew
Improvement | CATS-1307 | Update Hub UI Look to be consistent with Standard Look:InternalMovement/Create | Andinet Asaminew
Improvement | CATS-1295 | Update Hub UI to be consistent : Receiving | Andinet Asaminew
Improvement | CATS-1282 | Show grand total on HRD summary report. | robel alazar
Improvement | CATS-1281 | Filter 'Recent Requisitions' on EW Dashboard by rounds | nigus | requtition with hubassigned status is not visible
Improvement | CATS-1286 | Add Sub-total and Grand-total for Regional Request printout report. | robel alazar
Improvement | CATS-1283 | Grand total not shown on HRD summary by Region report. | Nathnael Ethan
Improvement | CATS-1280 | Filter 'Recent Requests' on EW Dashboard by Rounds. | nigus | comment should be added
Improvement | CATS-1265 | Add a grouping and sub total by Zone to Regional Request Detail | Nathnael Ethan
Improvement | CATS-1237 | Hub user permissions | robel alazar
Improvement | CATS-1205 | CATS cannot create TO for bids from selected locations. | robel alazar | test again
Improvement | CATS-1198 | When a regional Need assessment is rejected, add a feature to add a comment why it is rejected and if there is a possibility to attach a file which shows the corrected figures. | Nathnael Ethan
Improvement | CATS-1196 | 7. Send a notification (on screen) to regions when a need assessment is approved /rejected/ and when Hrd is created from need assessment. | nigus
Improvement | CATS-1188 | On hub dashboard check the stock status graph | robel alazar
Improvement | CATS-1179 | payment request - reference no should be printed on the letter which is sent to the finance. | nigus | passed
Improvement | CATS-1186 | Add delete and add new woreda to RFQ entry | Nathnael Ethan
Improvement | CATS-1175 | payment request. Please add allocated and dispatched amount in bag not in kg or MT | Nathnael Ethan | recheck amounts in bag and received qty, against dispatch at hubs
Improvement | CATS-1306 | Update Hub UI Look to be consistent with Standard Look: Hub Dashboard | Andinet Asaminew
Improvement | CATS-1312 | Update Hub UI Look to be consistent with Standard Look and make the page responsive(change html tbl to bootstrap grid) :Pages(Record new Loss and record new Adjustment) | Andinet Asaminew
New Feature | CATS-1288 | Assisted number of beneficiaries by age group per region | Nathnael Ethan
New Feature | CATS-1289 | Assisted number of beneficiaries by type of support report | robel alazar
New Feature | CATS-1193 | When a regional request is rejected, add a remark feature and if there is a possibility to attach a file which shows the corrected figures | robel alazar
New Feature | CATS-1170 | Add a letter template to the reporting list of payment request | nigus | Reference no. should be displayed for the selected transporters
New Feature | CATS-1301 | Data Entry status indicator for EW case team | nigus
New Feature | CATS-1303 | Data Entry status indicator for Procurement CTL | robel alazar
New Feature | CATS-1302 | Data Entry status indicator for LG CTL | Nathnael Ethan | incomplete ,chart is not displayed
New Feature | CATS-1304 | Data Entry status indicator for Finance CTL | Yonathan Weldeselassie
New Feature | CATS-1317 | Implement workflow module on requisition | Nathnael Ethan
Support request | CATS-1231 | Clicking more from notification menu takes to an empty list even if notification badge show items. | robel alazar
Support request | CATS-1232 | Clicking a link from the notification menu takes to a URL which is not working. | robel alazar
On Needs assessment detail ,season name should be displayed instead of id
Should be allowed to create more than one needs assessment for a region with d/t parameter (season ,type)
* Error on Dispatch detail